## 01 June 2016
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
234 | 3. Successful Futures | Review communication channels for Successful Futures as LAs report that information isn’t getting through to them via consortia (WG) | CR | Open
235 | 3. Successful Futures | Consider how SDF could input to the development of thinking about revisions to the assessment framework and to implement a two-way process (WG) | CR | Open
236 | 3. Successful Futures | Consider how SDF could input to the work in pioneer schools and their needs given the differing requirements (WG) | CR | Open
237 | 4. KS4 performance reporting | suppliers to confirm they are able to meet Wales’ requirements using the pre-Woolf discount codes list, which is different to the list in England | Suppliers | Open
238 | 4. KS4 performance reporting | WG to provide QAN list for specific qualifications where possible. | SA | Open
239 | 4. KS4 performance reporting | WG to send link to the letter about changes to KS4 performance reporting | SA | Open
240 | 4. KS4 performance reporting | WG to provide the methodology and a worked example for the Capped Points Score calculation. | SA | Open
241 | 4. KS4 performance reporting | WG to provide the mapping of DfE grades 1-9 to Wales’ grades | SA | Open
242 | 5. NDC 2017 Draft Specification | WG to consider the timing of the Baseline Assessment data collection | CH | Closed | 2016-07-29 | No changes for 2017 and the collection as a whole will be considered alongside the Successful Futures planning
243 | 6. WNT 2017 Draft Spec | CH to add ‘significance’ to Modular CBDS, NAW_A_COMP and WNT specification | CH | Closed | 2016-07-29 | Included in NAW_A_COMP 2017 v1.0 and WNT Specification 2017 v1.0
244 | 6. WNT 2017 Draft Spec | WG to relay this information to the Assessment Team | CH | Closed | 2016-06-02 | Concerns about infrastructure for the online adaptive tests fedback to the policy team. The Tests branch has assured us that this is all being considered as part of the project and that they are working with the Digital Unit on this.
245 | 7. School Workforce collection Update | WG to consider setting up an SDF to go through the School Workforce data collection requirements | CH | Open |  | Not appropriate at this stage - further updates to come later in 2016
246 | 8. AOB | MJ raised an issue regarding categorisation of EAL pupils to Capita. MJ informed the group that there is disparity between the English and Welsh models and Capita still allows ‘ENG’ to be used as home language / Capita to look into this issue. | Capita | Open
247 | 8. AOB: Class Size Exception Codes | CH to include changes in Modular CBDS and January PLASC 2017 specification. | CH | Closed | 2016-06-02 | Included in Modular CBDS v1617.1 School and PLASC 2017 specification v2.0

## 02 February 2016
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
218 | 3. PLASC 2017 draft specification | WG to feedback the need for further guidance on SEN data to the policy team. | CH | Closed | 2016-03-22 | Raised with policy team and confirmed that guidance is not due for an update yet
219 | 3. PLASC 2017 draft specification | JA to send WG the Northern Irish policy on SEN reporting. | John Ashworth | Closed | 2016-06-01 | JA sent on 1/6/16
220 | 4. EOTAS 2017 draft specification | CH to add LEA tag above the new Estab tag. | CH | Closed | 2016-04-01 | Specification updated
221 | 4. EOTAS 2017 draft specification | WG to arrange a separate meeting to discuss the EOTAS collection exclusions requirement. | RE | Open |  | In progress
222 | 4. EOTAS 2017 draft specification | CH to amend the EOTAS specification to include various pupil scenarios for exclusions from PRUs. | CH | Closed | 2016-04-01 | Specification updated
223 | 6. Post-16 collection | WG to organise a separate meeting / telephone conference to discuss the Post-16 collection. | RE | Closed | 2016-06-01 | Meeting provisionally booked for 27 July and to be discussed at 1 June meeting
224 | 7. Post-16 2016 Specification | CH to amend specification to include DOB in section 2.1. | CH | Closed | 2016-05-17 | Included in v4.0 of the 2016 specification
225 | 7. Post-16 2016 Specification | BM to send draft completion notes to SDF for comment prior to the collection. | BM | Closed | 2016-05-17 | Completion notes released by MW
226 | 7. Post-16 2016 Specification | BM to feedback thoughts on the programme level data to the rest of the policy team. | BM | Open | 2016-05-17 | Done
227 | 7. Post-16 2016 Specification | Suppliers to provide specific data items they suggest should be added to the mapping table. | Suppliers | Open
228 | 8. Key Stage 4 | Wales are now diverging further from England at KS4. Suppliers to confirm that their systems are ready to implement these changes and differences. | Suppliers | Open |  | Feedback received from Capita
229 | 10. CTF | Suppliers to consider paper from RM and provide feedback. | Suppliers | Closed | 2016-03-04 | Feedback received
230 | 10. CTF | WG to provide SDF with rules for the transfer of FPP data. | CH | Closed | 2016-08-05 | Included in NAW_A_COMP 2017 v2.0
231 | 11. Hwb | Hwb presentation and documents to be sent to SDF colleagues. | RE | Closed | 2016-03-02
232 | 12. Modular CBDS | WG to feedback discussion on the free breakfast data item to policy team and identify what the data is used for. | CH | Closed | 2016-03-29 | Discussion with policy team requires further thought. Will potentially be part of a change for 2018 collection so action closed for SDF.
233 | 13. AOB | WG to keep the XSLT release schedule as 0, 1, 2, 3. | CH | Closed | 2016-02-24 | Requested changes currently being tested

## 17 November 2015
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
202 | 2. Minutes, actions and matters arising from the meeting on 2 June 2015 | WG to confirm in writing the decisions regarding the collection of KS4 cohort data. | WG | Closed | 2016-02-02 | SH provided this at the SDF meeting and a link to the letter published online can be found in the minutes.
203 | 2. Minutes, actions and matters arising from the meeting on 2 June 2015 | Suppliers to confirm how the new discount codes have been integrated, in response to forthcoming email from CH. | Suppliers | Closed | 2016-02-02 | Closed as duplicated action 228
204 | 3.A. Foundation Phase Profile (FPP) update | AS to consider downgrading validation errors to queries that trigger for pupils in NCY1 who legitimately have no BA results. | WG - AS | Closed | 2016-03-01 | These will remain as errors.
205 | 3.A. Foundation Phase Profile (FPP) update | WG to identify scenarios and guidance for ‘non-standard’ pupils for the NDC-BA collection. | WG - AS | Closed | 2016-02-01 | Policy FAQs provide advice.
206 | 3.A. Foundation Phase Profile (FPP) update | AS to consider a BA report to help with validation. | WG - AS | Closed | 2016-05-10 | Done.
207 | 3.A. Foundation Phase Profile (FPP) update | AS to consider providing guidance to schools about: 1. NCY1 pupils who legitimately have no BA results and who trigger errors/queries in validation. 2. DOB ranges for pupils who should be included in the NDC-BA file. | WG - AS | Closed | 2016-05-21 | Guidance released 21.04.16
208 | 3.A. Foundation Phase Profile (FPP) update | AS to communicate plans for the 2017 collection to suppliers as early as possible. | WG - AS | Closed | 2016-05-19 | Spec 0.1 released 19.05.16
209 | 3.B. Foundation Phase Profile - CTF proposals | CH to clarify the CTF proposal for FPP, including rules for calculation of AOLs where ladder scores are not present, and share with SDF. | WG - CH | Closed | 2016-02-02 | Closed as incorporated into action 230
210 | 3.B. Foundation Phase Profile - CTF proposals | CH to liaise with DFE to try and ensure FPP requirements are included in the 2016 CTF specification. | WG - CH | Closed | 2016-01-13 | Included in spec
211 | 4. Post-16 collection, matters arising from 2015 and future collections | BM to ask the funding team to clarify the purpose of collecting the Programmes of Study and associated guided contact hours. | WG - BM | Closed | 2016-02-02 | Paper from Geoff sent to suppliers
212 | 4. Post-16 collection, matters arising from 2015 and future collections | WG to clarify which pupils are to be included in the Post-16 return. | WG - CH | Closed | 2016-05-17 | Included in v4.0 of the 2016 specification
213 | 4. Post-16 collection, matters arising from 2015 and future collections | WG to provide a timeline and outline of possible changes to the 2016 Post-16 collection. | WG - CH | Closed | 2015-11-27 | Email from CH sent 27/11/15 giving approximate timescales for communicating any changes
214 | 4. Post-16 collection, matters arising from 2015 and future collections | BM to provide a detailed proposal for the replacement of Learning Activities. | WG - BM | Closed | 2016-01-19 | Included in WED matching paper
215 | 5. School workforce collection discussion paper | GT to refine the school workforce collection requirement and update SDF. | WG - GT | Closed | 2016-05-25 | Update and papers supplied and to be discussed at 1 June meeting
216 | 6. AOB - SEN classifications | CH to include new requirement for SEN needs in January PLASC specification for 2017. | WG - CH | Closed | 2016-01-19 | Included in spec
217 | 6. AOB - SEN classifications | CH to feed back ‘school concern’ suggestion to policy team. | WG - CH | Closed | 2015-11-27 | Policy team confirmed 'school concern' will not be collected

## 2 June 2015
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
182 | 2. Minutes, actions and matters arising from the meeting on 10 February 2015 | Suppliers to confirm how the new discount codes have been integrated. | Suppliers | Closed | 2015-11-17 | Closed and re-opened as Action 203
183 | 2. Minutes, actions and matters arising from the meeting on 10 February 2015 | WG to add Validation CBDS to the 2015/16 SDF cycle. | WG - CH | Closed | 2015-09-17
184 | 2. Minutes, actions and matters arising from the meeting on 10 February 2015 | WG to send out PLASC Validation CBDS. | WG - CH | Closed | 2015-07-03
185 | 4. Foundation Phase Profile | WG to consider how the baseline assessment of children entering a setting after the NDC in May will be recorded for 2016/17 onwards. | WG - CS | Closed | 2015-07-13 | Agreement that any pupils entering a setting after the NDC in May will not be recorded in 2016
186 | 4. Foundation Phase Profile | WG to update the Specification to reflect the Handbook’s definition of ‘reception’. | WG - AS | Closed | 2015-07-13 | Spec only now refers to NCY R (and next year it will refer to NCY R and NCY 1, when revised outcome statements are valid for NCY 1).
187 | 4. Foundation Phase Profile | WG to clarify whether pupils joining from another education system have to have a baseline assessment. | WG - CS | Closed | 2015-07-13 | Only the first baseline assessment is considered statutory and should be returned to WG, schools may choose to re assess but this is not considered statutory
188 | 4. Foundation Phase Profile | WG to review the requirement for ‘result date’ and consult with SDF. | WG - CS | Closed | 2015-07-13 | New data item <dateofcompletion> added to the schema
189 | 4. Foundation Phase Profile | WG to consider creating a temporary solution for recording the baseline assessment for data collection in September 2015. | WG - CS | Closed | 2015-07-13 | Spreadsheet for schools to record baseline assessments sent to SDF for consideration on 04/09/2015
190 | 4. Foundation Phase Profile | WG to release final A_Comp. | WG - AS | Closed | 2015-07-13
191 | 5. NDC Draft Specification 2016 | WG to use a different colour to identify changes from the previous version of the May 2016 specification and to explain the colour coding. | WG - AS | Closed | 2015-07-13 | Green used to highlight changes from the last version in specification and A_Comp.
192 | 5. NDC Draft Specification 2016 | WG to consider the transfer of FPP data and to indicate in A_Comp, or elsewhere, if possible, which data schools may want to transfer via CTF (in advance of the CTF specification being available). | WG - AS | Closed | 2016-02-02 | Closed as incorporated into action 230
193 | 5. NDC Draft Specification 2016 | WG to clarify in 2.1.2 that the end of FP assessment remains unchanged. | WG - AS | Closed |  | Version 3.0 of the spec released 23/10/15
194 | 5. NDC Draft Specification 2016 | WG to be explicit in A_Comp, for the avoidance of doubt, about which fields should have a value or be null. | WG - AS | Closed |  | Version 2.0 of A_COMP released 23/10/15
195 | 5. NDC Draft Specification 2016 | WG to update the Specification to identify that the FEWBES item in the KS4/KS5 container only relates to KS4. | WG - AS | Closed | 2015-07-13 | Spec clarifies that it relates to KS4 pupils only.
196 | 5. NDC Draft Specification 2016 | WG to consider whether NCyear 11 and/or aged 15 are both required and amend specification if necessary. | WG - AS | Closed | 2015-09-17 | Confirmed that NCyear 11 and/or aged 15 are both still required for NDC 15/16.
197 | 5. NDC Draft Specification 2016 | WG to provide a spreadsheet with a full list of ladders separately to the A_Comp and handbook. | WG - CS | Closed | 2015-07-13 | Issued on 13/07/2015
198 | 5. NDC Draft Specification 2016 | WG to circulate the handbook and presentation to suppliers. | WG - CS | Closed | 2015-07-13 | Issued on 13/07/2015
199 | 6. AOB | SDF cycle to flag any meetings that may be cancelled. | WG - RE | Closed | 2015-09-17
200 | 6. AOB | WG to advise whether the pupil count will use January or May data for KS4 reporting. | WG - KAS | Closed | 2015-11-17 | Closed and replaced with 202
201 | 6. AOB | WG to electronically circulate the document “Measuring secondary school performance in Wales”. | WG - RE | Closed | 2015-09-17

## 10 February 2015
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
159 | 3 Foundation Phase Profile and Curriculum Review | WG to circulate the Foundation Phase Profile User Guide when available. | WG - CS | Closed |  | Uploaded to DEWi - 20/02/2015
160 | 3 Foundation Phase Profile and Curriculum Review | WG to consider children who cannot achieve a skill, e.g. disapplication when creating the skill ladders | WG - CS | Closed | 2015-05-19 | 15/04/15 - Disapplication taken into account in draft A_Comp. Reviewing the results of the trial from Special Schools, no issues raised. Will be discussed 02/06/2015
161 | 3 Foundation Phase Profile and Curriculum Review | WG to request information from DfE about reporting from 0 years of age. | WG - CHo | Closed | 2015-02-10 | Part of CS research
162 | 3 Foundation Phase Profile and Curriculum Review | WG to arrange a meeting with suppliers after the pilot and before August to discuss reporting | WG - CS | Closed | 2015-05-19 | Near final draft will be available from the 14 May (will be proof reading at this point). We will therefore be able to confirm ladders and which outcomes have statements. FPP will be signed off by Minister on 3 June, happy to circulate following this. Meeting to replace June SDF.
163 | 3 Foundation Phase Profile and Curriculum Review | WG to complete a draft specification and A_Comp by the next meeting, 10 March. | WG - JA | Closed | 2015-05-22 | 06/3/15 - Draft A - COMP added to DEWi, V0.1 22/05/15 - Draft Spec added to DEWi, V0.1
164 | 4 NDC & National Test Update | WG to circulate the CSV specification | WG - CHo | Closed | 2015-05-19 | Uploaded to DEWi
165 | 4 NDC & National Test Update | WG to keep suppliers informed on actions for import files. | WG - CHo | Closed | 2015-07-22
166 | 4 NDC & National Test Update | WG to circulate correspondence with instructions for deleting the data. | WG - CHo | Closed | 2015-07-22 | Incorrect data sucessfully deleted from all systems.
167 | 5 Interventions Monitoring | WG to consider the role of the LA, data collection and CTF for monitoring interventions. | WG | Open
168 | 5 Interventions Monitoring | WG to consider defining data for CBDS. | WG | Open
169 | 5 Interventions Monitoring | WG to circulate key dates of the Interventions Monitoring programme | WG | Open
170 | 6 Post-16 2016 | WG to confirm release dates for look up tables | WG - SJ | Closed | 2015-05-29 | Email sent with release dates
171 | 6 Post-16 2016 | WG to amend on roll date description to include ‘during previous academic year’. | WG - SJ | Closed | 2015-04-29 | 2015 and 2016 Specifications released
172 | 6 Post-16 2016 | WG to add detail to the specification for the point in time that NCYear should be taken. | WG - SJ | Closed | 2015-04-29 | 2015 and 2016 Specifications released
173 | 6 Post-16 2016 | LAs to find out if it is recorded if pupils start early. | LAs | Open |  | No feedback received yet
174 | 6 Post-16 2016 | WG to send guidance on the Post 16 collection to LAs | WG - NHO | Closed | 2015-06-16
175 | 6 Post-16 2016 | WG to confirm with suppliers how the XSLT will differentiate between Post-16 2015 and 2016. | WG - SJ | Closed | 2015-05-29 | Email sent with differentiations
176 | 6 Post-16 2016 | WG to amend information on duplicate learning activities. | WG - SJ | Closed | 2015-04-29 | Updated Specification released
177 | 7 PLASC spec 2016 | Suppliers to review and agree the PLASC specification by the next meeting, scheduled for 10 March 2015. | Suppliers | Closed | 2015-03-05 | Specification reviewed and agreed
178 | 8 Attendance spec 2016 | Suppliers to review and agree the Attendance specification by the next meeting, scheduled for 10 March 2015. | Suppliers | Closed | 2015-03-05 | Specification reviewed and agreed
179 | 9 EOTAS spec 2016 | Suppliers to review and agree the EOTAS specification by next meeting, scheduled for 10 March 2015. | Suppliers | Closed | 2015-03-05 | Specification reviewed and agreed
180 | 10 AOB | WG to circulate 2015/16 SDF cycle | WG - CHo | Closed | 2015-05-19 | Uploaded to DEWi - 19/05/2015
181 | 10 AOB | WG to consider the timing of CTF versioning and ensure that LRS is using the right version for ULN files. | WG - CHo | Closed | 2015-05-19 | Included in Jan PLASC development request

## 11 November 2014
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
147 | Minutes, actions and matters arising from the meeting on 4 June, 2014 | WG to amend Post-16 guidance notes to include year taught definition | WG -SJ | Closed | 2015-01-27 | To be discussed at SDF
148 | Post-16 2016 | AO to clarify what key skills data is needed from schools. | WG - AO | Closed | 2015-01-09 | Clarification added to completion notes (Section 6)
149 | Post-16 2016 | Spec to be updated to show which look-ups go with which collection. | WG - SJ | Closed | 2015-01-26 | Revised spec sent
150 | Post-16 2016 | WG to amend spec to state suppliers are to make it easier to add providers. | WG - SJ | Closed | 2015-04-29 | Spec to be updated in next version 27/01/2015
151 | Post-16 2014 | AO to confirm how duplicate learning activities should be dealt with (school timetabling). | WG - AO | Closed | 2015-01-26 | Revised spec sent
152 | Post-16 2014 | SJ to update Spec and completion notes with a definition of a learning activity. | WG - SJ | Closed | 2015-02-10 | Spec updated 26/01/2015, completion notes to be published
153 | Post-16 2014 | AO to confirm if Welsh schools can choose to deliver the two-year A-levels and to check funding arrangements for these courses. | WG - AO | Closed | 2015-02-10 | Policy confirmed two year A Levels not available in Wales
154 | Post-16 2014 | WG to follow up on new attendance guidance and ensure it covers dual registration. | WG | Closed |  | New attendance guidance is being consulted on in early 2015.
155 | Issues arising during the collection | Suppliers to update points of contact. | Suppliers | Closed | 2015-02-10 | All suppliers updated points of contact
156 | National Tests Update | CHo to get consensus across all LAs for the best format for import files in 2015. | WG - CHo | Closed | 2015-06-02 | Partial CTF format agreed by all suppliers 02/06/2015
157 | National Tests Update | Suppliers to consider the deletion of 2013 data and feedback on any issues. | Suppliers | Closed | 2015-02-10 | Email sent to SDF group 19/01/15
158 | National Tests Update | CHo to provide clear guidance on how <, >, X and D scores are to be included when aggregating results. | WG - CHo | Closed | 2015-01-26 | Email sent to LAs 26/01/15

## 4 June 2014
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
122 | 1 Minutes, actions and matters arising from the meeting on 18 March 2014 | WG to amend procedures to ensure that guidance notes for all collections are made available as early as possible on the SDF site. | WG | Closed | 2014-11-01 | Implemented for Post-16
123 | 3 EYDAF and Curriculum Review | WG to consider impact of EYDAF on CTF. | WG | Closed |  | CTF paper for FPP in progress
124 | 4 NDC & National Tests 2015 | Suppliers to confirm that this change can be implemented. | Suppliers | Closed | 2014-12-19 | Confirmation from Advanced Learning and Capita received - 10/11/2014 RM - 19/12/2014
125 | 4 NDC & National Tests 2015 | CHo to add the import file structure to the specification and publish on the SDF site. | WG - CHo | Closed | 2014-06-13 | Released to SDF site
126 | 4 NDC & National Tests 2015 | CHo to ensure that historical components are retained in the Excel versions of A_COMP and that only the current year's components are included in the specification. | WG - CHo | Closed | 2014-06-13 | Released to SDF site
127 | 4 NDC & National Tests 2015 | WG to provide 2013 test data to LAs. | WG | Closed | 2015-01-13
128 | 4 NDC & National Tests 2015 | WG to provide clear communications on the revision of 2013 reading test scores. | WG | Closed | 2015-02-10 | Email sent 19/01/2015
129 | 4 NDC & National Tests 2015 | WG to work with suppliers to ensure revised scores are delivered to schools as soon as possible with clear instructions. | WG | Closed | 2015-07-22 | Provided to LAs but without an automated process. Incorrect data sucessfully deleted from all systems.
130 | 4 NDC & National Tests 2015 | SH to distribute revised quartiles. | WG - SH | Closed |  | Issued for 2015
131 | 4 NDC & National Tests 2015 | WG to respond to Mike's query. [language of test] | WG | Closed | 2014-06-06 | KAS confirmed data to be submitted for this pupil.
132 | 4 NDC & National Tests 2015 | CHo to confirm xsd filesets for summer 2015. | WG - CHo | Closed | 2014-06-10 | Confirmed by email.
133 | 5 Post-16 2015 | AO to include line in specification that software does not have to validate activities within programmes. | WG - AO | Closed | 2014-07-15 | Included in Post-16 spec (Version 2.0)
134 | 5 Post-16 2015 | AO to provide LAs information on the changes to the post-16 collection. | WG - AO | Closed | 2014-06-12 | Email from Sian James to LAs
135 | 5 Post-16 2015 | WG to consider validation rules. | WG - SJ | Closed | 2014-08-04 | Validation CBDS v1516.0.0 released to SDF site, including validation rules for some programmes.
136 | 5 Post-16 2015 | WG to clarify in the specification if subjects are being recorded but not used for performance. | WG - AO | Closed | 2014-07-15 | Policy team confirmed that data on all activities from 01/09 each year are to be included in the return
137 | 5 Post-16 2016 | Suppliers to notify schools not to change the year taught data item until September. | Suppliers | Closed | 2014-12-19 | Confirmation from Advanced Learning and Capita received.
138 | 6 2014 Performance Tables | SH to share stakeholder survey results with SDF. | WG - SH | Closed | 2014-11-10 | Link to stakeholder survey sent to SDF mailing list.
139 | 6 2014 Performance Tables | SH to share the discounting table for Wales. | WG - SH | Closed | 2015-05-29 | 19/11/2014 - We will share the latest (2014) list with suppliers as soon as the 2014 exercise is closed. Published on 29/05/2015, 2015 and 2016 list will be the same as 2014.
140 | 6 2014 Performance Tables | SH to review the outcome and advise SDF of any implications for summary reports that suppliers may provide in their systems. | WG - SH | Closed |  | 19/11/2014 - impact of survey results will happen in 2016
141 | 7 EOTAS 2016 | WG to consider the double counting issue when including exclusions in the EOTAS 2016 draft specification. | WG - CHo | Closed | 2015-01-27 | Spec sent with papers for 10/02/2015 SDF meeting
142 | 8 XSLT fileset naming convention | WG to trial release note with next release of new xslt filesets. | WG | Closed |  | Completed for Jan 2015 XSLT
143 | 9 SDF Cycle | CHo to send out more information on the changes. | WG - CHo | Closed | 2014-06-09 | Email with details of the change sent to SDF
144 | 11 AOB | WG to contact LAs for feedback on this item. [penalty notices] | WG - CHo | Closed | 2014-12-15 | Email sent to LA's circulated to SDF contacts 15/12/2014
145 | 11 AOB | CHo to get in touch with LH to resolve the query. [action 103, exceptions] | WG - CHo | Closed | 2014-06-05 | Query passed to policy team for response
146 | 11 AOB | CHo to get in touch with LH to resolve the query. [ULN] | WG - CHo | Closed | 2014-06-18 | Resolved between WG, RM, LA and school

## 18 March 2014
Ref | Agenda Item | Action | Owner | Status | Resolution Date | Update
100 | 3. Jan. PLASC 2015 Amended Specification | Review School Governance in PLASC after PLASC 2015 | WG - CHo | Closed | 2016-02-01 | To be reviewed for 2017 spec, due in February 2016. No change to school federations in PLASC
104 | 3. Jan. PLASC 2015 Amended Specification | Arrange a review of summary reports | WG - CHo | Open |  | In progress
105 | 4. EOTAS 2015 Amended Specification | Provide information on EOTAS funding and the prevention of double counting between main and EOTAS provisions | WG - SHu | Closed | 2014-06-04 | SH confirmed that there are a number of checks in place to prevent double counting at the SDF meeting on 04/06/14.
108 | 4. EOTAS 2015 Amended Specification | Provide guidance on SEN rankings in PLASC and EOTAS | WG - CHo | Closed | 2014-06-04 | CHo confirmed that this will be included in guidance for PLASC & EOTAS 2015 at the SDF meeting on 04/06/14.
110 | 5. NDC and National Tests | WG confirm file formats for NDC file downloads from DEWi | WG - CHo | Closed | 10/02/2015 See ref 164 | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with suppliers to ensure LAs are able to import tests data for 2015
112 | 6. Post-16 2015 Draft Specification | WG inform schools of the post-16 changes | WG - AO | Closed | 2014-11-11 | AO confirmed at SDF on 11 November that meetings have been held with schools and the completion notes will cover any changes.
114 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to be made available to suppliers/ uploaded to DEWi SDF | WG - AO | Closed | 2014-07-01 | Completion notes for 2014 released to SDF site
115 | 6. Post-16 2015 Draft Specification | New summary reports should include blank/zero lines | WG - AO | Closed | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
116 | 6. Post-16 2015 Draft Specification | Post-16 Technical Completion Notes to state which pupils should be included in the return | WG - AO | Closed | 2014-07-01 | Included in completion notes
117 | 6. Post-16 2015 Draft Specification | WG to provide guidance on mature learners, the P-16 collection and UPNs | WG | Closed | 2015-01-05 | Included in completion notes for 2015
118 | 6. Post-16 2015 Draft Specification | WG to provide mapping table to the SDF and LA Data/IMS teams | WG - AO | Closed | 2014-06-04 | AO advised that this would not be feasible at the SDF meeting on 04/06/14.
119 | 6. Post-16 2015 Draft Specification | A link to the mapping table to be included in Post-16 Completion Notes | WG - AO | Closed | 2014-06-04 | As action 118.
120 | 7. XSLT fileset naming convention | WG to review fileset numbering | WG - CHo | Closed | 2014-06-04 | Discussed at the SDF meeting on 04/06/14 and agreed to trial new fileset release note with January 2015 xslt files.
121 | 8. A.O.B. | WG to research the issue of commas within pupil names | WG - CHo | Closed | 2015-05-19 | CHo requested more information on this at the SDF meeting on 04/06/14 and will now work with Method4 to ensure the issue can be resolved.

## 11 February 2014
Ref | Agenda item | Action | Owner | Status | Resolution Date | Update
92 | 6 Post-16 | Provide a mapping table for Activities to Programmes | WG - AO | Closed | 2014-06-04 | Duplication of actions 118 and 119.
96 | 10 Response Times | Revised approach to response times to be reviewed in 3 months | WG - CHo | Closed | 2014-06-04 | Reviewed at SDF meeting on 04/06/14 and agreed that there has been an improvement and that the action could be re-opened if necessary in future.
97 | 10 Response Times | Investigate the use the of issues log within DEWi for supplier queries | WG - CHo | Closed | 2014-06-04 | Can be re-opened in future if deemed necessary, see action 96.

## 1 July 2013
Ref | Agenda item | Action | Owner | Status | Resolution Date | Update
68 | 7 Any Other Business | Provide PLASC data to Cardiff and Swansea to investigate discrepancies on the calculation of fixed-term exclusions | WG - SHu/MS | Closed | 2014-07-01 | Three local authorities were sent their data to compare in July, but we have still not heard back from them 10/11/14.

## All Open Actions
Ref | Date Raised | Agenda Item | Action | Owner | Update
104 | 2014-03-18 | 3. Jan. PLASC 2015 Amended Specification | Arrange a review of summary reports | CHo | In progress
167 | 2015-02-10 | 5 Interventions Monitoring | WG to consider the role of the LA, data collection and CTF for monitoring interventions. | WG
168 | 2015-02-10 | 5 Interventions Monitoring | WG to consider defining data for CBDS. | WG
169 | 2015-02-10 | 5 Interventions Monitoring | WG to circulate key dates of the Interventions Monitoring programme | WG
173 | 2015-02-10 | 6 Post-16 2016 | LAs to find out if it is recorded if pupils start early. | LAs | No feedback received yet
221 | 2016-02-02 | 4. EOTAS 2017 draft specification | WG to arrange a separate meeting to discuss the EOTAS collection exclusions requirement. | RE | In progress
227 | 2016-02-02 | 7. Post-16 2016 Specification | Suppliers to provide specific data items they suggest should be added to the mapping table. | Suppliers
228 | 2016-02-02 | 8. Key Stage 4 | Wales are now diverging further from England at KS4. Suppliers to confirm that their systems are ready to implement these changes and differences. | Suppliers | Feedback received from Capita
234 | 2016-06-01 | 3. Successful Futures | Review communication channels for Successful Futures as LAs report that information isn’t getting through to them via consortia (WG) | CR
235 | 2016-06-01 | 3. Successful Futures | Consider how SDF could input to the development of thinking about revisions to the assessment framework and to implement a two-way process (WG) | CR
236 | 2016-06-01 | 3. Successful Futures | Consider how SDF could input to the work in pioneer schools and their needs given the differing requirements (WG) | CR
237 | 2016-06-01 | 4. KS4 performance reporting | suppliers to confirm they are able to meet Wales’ requirements using the pre-Woolf discount codes list, which is different to the list in England | Suppliers
238 | 2016-06-01 | 4. KS4 performance reporting | WG to provide QAN list for specific qualifications where possible. | SA
239 | 2016-06-01 | 4. KS4 performance reporting | WG to send link to the letter about changes to KS4 performance reporting | SA
240 | 2016-06-01 | 4. KS4 performance reporting | WG to provide the methodology and a worked example for the Capped Points Score calculation. | SA
241 | 2016-06-01 | 4. KS4 performance reporting | WG to provide the mapping of DfE grades 1-9 to Wales’ grades | SA
245 | 2016-06-01 | 7. School Workforce collection Update | WG to consider setting up an SDF to go through the School Workforce data collection requirements | CH | Not appropriate at this stage - further updates to come later in 2016
246 | 2016-06-01 | 8. AOB | MJ raised an issue regarding categorisation of EAL pupils to Capita. MJ informed the group that there is disparity between the English and Welsh models and Capita still allows ‘ENG’ to be used as home language / Capita to look into this issue. | Capita

## Actions closed after 01.06.2016
Ref | Date Raised | Agenda item | Action | Owner | Resolution Date | Update
219 | 2016-02-02 | 3. PLASC 2017 draft specification | JA to send WG the Northern Irish policy on SEN reporting. | John Ashworth | 2016-06-01 | JA sent on 1/6/16
230 | 2016-02-02 | 10. CTF | WG to provide SDF with rules for the transfer of FPP data. | CH | 2016-08-05 | Included in NAW_A_COMP 2017 v2.0
242 | 2016-06-01 | 5. NDC 2017 Draft Specification | WG to consider the timing of the Baseline Assessment data collection | CH | 2016-07-29 | No changes for 2017 and the collection as a whole will be considered alongside the Successful Futures planning
243 | 2016-06-01 | 6. WNT 2017 Draft Spec | CH to add ‘significance’ to Modular CBDS, NAW_A_COMP and WNT specification | CH | 2016-07-29 | Included in NAW_A_COMP 2017 v1.0 and WNT Specification 2017 v1.0
244 | 2016-06-01 | 6. WNT 2017 Draft Spec | WG to relay this information to the Assessment Team | CH | 2016-06-02 | Concerns about infrastructure for the online adaptive tests fedback to the policy team. The Tests branch has assured us that this is all being considered as part of the project and that they are working with the Digital Unit on this.
247 | 2016-06-01 | 8. AOB: Class Size Exception Codes | CH to include changes in Modular CBDS and January PLASC 2017 specification. | CH | 2016-06-02 | Included in Modular CBDS v1617.1 School and PLASC 2017 specification v2.0