## Sheet1
Task Name | Duration | Start | Finish | Resource | Updates
CTF15 draft release to suppliers | 1 day | 2015-05-01 | 2015-05-01 | DFE
A_COMP 2015 Review | 44 days | 2015-02-02 | 2015-04-02 | WG
Develop January PLASC and EOTAS 2016
Specification | 13 days | 2015-01-23 | 2015-02-10 | WG
Draft specification release | 1 day | 2015-02-10 | 2015-02-10 | WG
Supplier review period | 21 days | 2015-02-10 | 2015-03-10 | Suppliers
Version 1 specification release | 1 day | 2015-03-11 | 2015-03-11 | WG
Release validation CBDS | 1 day | 2015-07-03 | 2015-07-03 | WG
xslt development | 23 days | 2015-06-15 | 2015-07-15 | WG
Draft fileset release | 1 day | 2015-07-15 | 2015-07-15 | WG
Supplier review period | 11 days | 2015-07-15 | 2015-07-30 | Suppliers
Final fileset release | 1 day | 2015-07-31 | 2015-07-31 | WG
DEWi developments | 1 day | 2015-08-02 | 2015-08-02 | M4/WG
Release to supplier test DEWi sites for PLASC & EOTAS 2015 | 1 day | 2015-08-02 | 2015-08-02 | M4/WG
Review and update the ULN collection, also taking into account of CTF changes | 26 days | 2015-03-11 | 2015-04-15 | WG
Supplier version of completion notes released | 1 day | 2015-06-22 | 2015-06-22 | WG
Develop Attendance 2016
Specification | 13 days | 2015-01-23 | 2015-02-10 | WG
Draft specification release | 1 day | 2015-02-10 | 2015-02-10 | WG
Supplier review period | 21 days | 2015-02-10 | 2015-03-10 | Suppliers
Version 1 specification release | 1 day | 2015-03-11 | 2015-03-11 | WG
Release validation CBDS | 1 day | 2015-08-24 | 2015-08-24 | WG
xslt development | 14 days | 2015-09-09 | 2015-09-28 | WG
Draft fileset release | 1 day | 2015-09-09 | 2015-09-09 | WG
Supplier review period | 11 days | 2015-09-10 | 2015-09-24 | Suppliers
Final fileset release | 1 day | 2015-09-28 | 2015-09-28 | WG
DEWi developments | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Release to supplier test DEWi sites for Attendance & NDC 2015 | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Supplier version of completion notes released | 1 day | 2015-09-28 | 2015-09-28 | WG
Spring SDF meetings
Software Development Forum meeting* | 1 day | 2015-02-10 | 2015-02-10 | Suppliers/WG
Spec review period: PLASC, EOTAS & Attendance 2015 | 21 days | 2015-02-10 | 2015-03-10 | Suppliers
Software Development Forum meeting* | 1 day | 2015-03-10 | 2015-03-10 | Suppliers/WG | Cancelled
CTF15 final release to suppliers | 1 day | 2015-07-01 | 2015-07-01 | DFE
Develop Post-16 October 2015
Specification | 23 days | 2014-05-01 | 2014-06-02 | WG
Draft specification release | 1 day | 2014-06-02 | 2014-06-02 | WG
Supplier review period | 23 days | 2014-06-03 | 2014-07-03 | Suppliers
Version 1 specification release | 1 day | 2014-07-03 | 2014-07-03 | WG
Release validation CBDS | 1 day | 2014-08-04 | 2014-08-04 | WG
xslt development | 24 days | 2014-08-08 | 2014-09-10 | WG
Draft fileset release | 1 day | 2014-09-11 | 2014-09-11 | WG
Supplier review period | 11 days | 2014-09-11 | 2014-09-25 | Suppliers
Final fileset release | 1 day | 2014-09-26 | 2014-09-26 | WG
Update of fileset release with 14/15 look-ups | 1 day | 2014-10-01 | 2014-10-01 | WG
DEWi developments | 5 days | 2015-07-07 | 2015-07-11 | M4/WG
Release to supplier test DEWi sites for Post-16 October 2015 | 1 day | 2015-07-20 | 2015-07-20 | M4/WG
Release update with look-ups to supplier test DEWi site Post-16 October 2015 | 1 day | 2015-05-21 | 2015-05-21 | M4/WG
Supplier version of completion notes released | 1 day | 2015-09-28 | 2015-09-28 | WG
Develop Post-16 October 2016
Specification | 23 days | 2014-10-10 | 2014-11-11 | WG
Draft specification release | 1 day | 2014-11-11 | 2014-11-11 | WG
Supplier review period | 23 days | 2014-11-11 | 2014-12-11 | Suppliers
Version 1 specification release | 1 day | 2015-02-10 | 2015-02-10 | WG
Release validation CBDS | 1 day | 2015-01-23 | 2015-01-23 | WG
xslt development | 8 days | 2015-02-11 | 2015-02-20 | WG
Draft fileset release (Schema only) | 1 day | 2015-05-29 | 2015-05-29 | WG
Supplier review period | 10 days | 2015-02-23 | 2015-03-06 | Suppliers
Final fileset release (Validation and Summary) | 1 day | 2015-10-20 | 2015-10-20 | WG
Update of fileset release with 15/16 look-ups | 1 day | 2015-10-20 | 2015-10-20 | WG
DEWi developments | 11 days | 2015-07-27 | 2015-08-10 | M4/WG
Release to supplier test DEWi sites for Post-16 October 2016 | 1 day | 2015-08-25 | 2015-08-25 | M4/WG
Release update with look-ups to supplier test DEWi site Post-16 October 2016 | 1 day | 2016-04-30 | 2016-04-30 | M4/WG
Supplier version of completion notes released | 1 day | 2015-03-09 | 2015-03-09 | WG
Develop Post-16 October 2017
Specification | 22 days | 2015-09-07 | 2015-10-06 | WG
Draft specification release | 1 day | 2015-10-06 | 2015-10-06 | WG
Supplier review period | 30 days | 2015-10-06 | 2015-11-17 | Suppliers
Version 1 specification release | 1 day | 2015-10-27 | 2015-10-27 | WG
Release validation CBDS | 1 day | 2015-10-27 | 2015-10-27 | WG
xslt development | 8 days | 2015-11-27 | 2015-11-27 | WG
Draft fileset release | 1 day | 2015-11-30 | 2015-11-30 | WG
Supplier review period | 10 days | 2015-11-30 | 2015-12-14 | Suppliers
Final fileset release | 1 day | 2015-12-14 | 2015-12-14 | WG
Update of fileset release with 16/17 look-ups | 1 day | 2016-10-31 | 2016-10-31 | WG
DEWi developments | 11 days | 2016-07-04 | 2016-07-18 | M4/WG
Release to supplier test DEWi sites for Post-16 October 2016 | 1 day | 2016-08-25 | 2016-08-25 | M4/WG
Release update with look-ups to supplier test DEWi site Post-16 October 2016 | 1 day | 2017-04-30 | 2017-04-30 | M4/WG
Supplier version of completion notes released | 1 day | 2015-10-27 | 2015-10-27 | WG
CBDS (standard) change cycle
CBDS 1516 published - Pupil/School | 1 day | 2015-05-29 | 2015-05-29 | WG
A_COMP published | 1 day | 2015-05-29 | 2015-05-29 | WG
WED 2015 on DEWi
WED 2015 DEWi development | 10 days | 2015-04-14 | 2015-04-27 | M4/WG
WED 2015 DEWi UAT | 5 days | 2015-04-28 | 2015-05-04 | M4/WG
WED 2015 DEWi rework | 3 days | 2015-05-06 | 2015-05-08 | M4/WG
WED 2015 Release to test DEWi site | 1 day | 2015-05-11 | 2015-05-11 | M4/WG
WED 2015 DEWi UAT on test site | 2 days | 2015-05-13 | 2015-05-14 | M4/WG
WED 2015 Release to live DEWi site | 1 day | 2015-05-15 | 2015-05-15 | M4/WG
Develop NDC 2016
Specification | 23 days | 2015-05-01 | 2015-06-02 | WG
Draft specification release | 1 day | 2015-06-02 | 2015-06-02 | WG
Supplier review period | 23 days | 2015-06-02 | 2015-07-02 | Suppliers
Version 1 specification release | 1 day | 2015-07-02 | 2015-07-02 | WG
Release validation CBDS | 1 day | 2015-08-24 | 2015-08-24 | WG
xslt development | 14 days | 2015-09-09 | 2015-09-28 | WG
Draft fileset release | 1 day | 2015-09-09 | 2015-09-09 | WG
Supplier review period | 11 days | 2015-09-10 | 2015-09-24 | Suppliers
Final fileset release | 1 day | 2015-09-28 | 2015-09-28 | WG
DEWi developments | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Release to supplier test DEWi sites for Attendance & NDC 2015 | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Supplier version of completion notes released | 1 day | 2015-09-28 | 2015-09-28 | WG
Develop WNT 2016
Specification | 23 days | 2015-05-02 | 2015-06-02 | WG
Draft specification release | 1 day | 2015-06-02 | 2015-06-02 | WG
Supplier review period | 23 days | 2015-06-02 | 2015-07-02 | Suppliers
Version 1 specification release | 1 day | 2015-07-02 | 2015-07-02 | WG
Release validation CBDS | 1 day | 2015-08-24 | 2015-08-24 | WG
xslt development | 14 days | 2015-09-09 | 2015-09-28 | WG
Draft fileset release | 1 day | 2015-09-09 | 2015-09-09 | WG
Supplier review period | 11 days | 2015-09-10 | 2015-09-24 | Suppliers
Final fileset release | 1 day | 2015-09-28 | 2015-09-28 | WG
DEWi developments | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Release to supplier test DEWi sites for Attendance & NDC 2015 | 1 day | 2015-10-05 | 2015-10-05 | M4/WG
Supplier version of completion notes released | 1 day | 2015-09-28 | 2015-09-28 | WG
Summer SDF meeting
Software Development Forum meeting | 1 day | 2015-06-02 | 2015-06-02 | Suppliers/WG
DEWI user audit | 19 days | 2015-09-01 | 2015-09-25 | WG
Autumn SDF meetings
Software Development Forum meeting* | 1 day | 2015-10-06 | 2015-10-06 | Suppliers/WG | Cancelled
Software Development Forum meeting* | 1 day | 2015-11-17 | 2015-11-17 | Suppliers/WG
CTF16 consultation | 21 days | 2015-12-01 | 2015-12-29 | WG
*Potential to be cancelled