## Sheet1
Task Name | Start | Finish | Resource | Updates
CTF16 draft release to suppliers |  | 2016-02-01 | DFE
A_COMP 2016 Review | 2016-02-01 | 2016-04-04 | WG
Develop January PLASC and EOTAS 2017
Specification | 2016-01-04 | 2016-02-02 | WG
Draft specification release |  | 2016-02-02 | WG
Supplier review period | 2016-02-03 | 2016-03-07 | Suppliers
Version 1 specification release |  | 2016-03-08 | WG
Release validation CBDS |  | 2016-07-04 | WG
xslt development | 2016-06-17 | 2016-07-15 | WG
Draft fileset release |  | 2016-07-15 | WG
Supplier review period | 2016-07-15 | 2016-07-28 | Suppliers
Final fileset release |  | 2016-07-29 | WG
DEWi developments | 2016-07-15 | 2016-07-29 | M4/WG
Release to supplier test DEWi sites |  | 2016-08-01 | M4/WG
Review and update the ULN collection, also taking into account of CTF changes |  | 2016-04-01 | WG
Supplier version of completion notes released |  | 2016-07-29 | WG
Develop Attendance 2017
Specification | 2016-01-04 | 2016-02-02 | WG
Draft specification release |  | 2016-02-02 | WG
Supplier review period | 2016-02-03 | 2016-03-07 | Suppliers
Version 1 specification release |  | 2016-03-08 | WG
Release validation CBDS |  | 2016-08-26 | WG
xslt development | 2016-08-30 | 2016-09-23 | WG
Draft fileset release |  | 2016-09-23 | WG
Supplier review period | 2016-09-23 | 2016-10-06 | Suppliers
Final fileset release |  | 2016-10-07 | WG
DEWi developments | 2016-08-30 | 2016-10-07 | M4/WG
Release to supplier test DEWi sites |  | 2016-10-07 | M4/WG
Supplier version of completion notes released |  | 2016-10-07 | WG
Spring SDF meetings
Software Development Forum meeting* |  | 2016-02-02 | Suppliers/WG
Spec review period: PLASC, EOTAS & Attendance | 2016-02-02 | 2016-03-08 | Suppliers
Software Development Forum meeting* |  | 2016-03-08 | Suppliers/WG
CTF16 final release to suppliers |  | 2016-07-04 | DFE
Develop Post-16 October 2017
Specification | 2016-01-04 | 2016-02-02 | WG
Draft specification release |  | 2016-02-02 | WG
Supplier review period | 2016-02-03 | 2016-03-07 | Suppliers
Version 1 specification release |  | 2016-03-08 | WG
Release validation CBDS |  | 2016-03-29 | WG
xslt development | 2016-04-04 | 2016-04-22 | WG
Draft fileset release |  | 2016-04-22 | WG
Supplier review period | 2016-04-22 | 2016-05-06 | Suppliers
Final fileset release |  | 2016-05-06 | WG
Update of fileset release with look-ups |  | 2016-10-28 | WG
DEWi developments | 2016-08-08 | 2016-08-19 | M4/WG
Release to supplier test DEWi sites |  | 2016-08-19 | M4/WG
Release update with look-ups to supplier test DEWi site |  | 2017-04-28 | M4/WG
Supplier version of completion notes released |  | 2016-03-31 | WG
CBDS (standard) change cycle
CBDS 1617 published - Pupil/School |  | 2016-04-04 | WG
A_COMP published |  | 2016-04-04 | WG
WED 2016 on DEWi
DEWi development | 2016-04-11 | 2016-04-29 | M4/WG
DEWi UAT | 2016-05-04 | 2016-05-06 | M4/WG
DEWi rework | 2016-05-09 | 2016-05-11 | M4/WG
Release to test DEWi site |  | 2016-05-12 | M4/WG
DEWi UAT on test site | 2016-05-12 | 2016-05-13 | M4/WG
Release to live DEWi site |  | 2016-05-16 | M4/WG
Develop NDC 2017
Specification | 2016-05-03 | 2016-06-01 | WG
Draft specification release |  | 2016-06-01 | WG
Supplier review period | 2016-06-02 | 2016-07-05 | Suppliers
Version 1 specification release |  | 2016-07-05 | WG
Release validation CBDS |  | 2016-08-26 | WG
xslt development | 2016-08-30 | 2016-09-23 | WG
Draft fileset release |  | 2016-09-23 | WG
Supplier review period | 2016-09-23 | 2016-10-06 | Suppliers
Final fileset release |  | 2016-10-07 | WG
DEWi developments | 2016-08-30 | 2016-10-07 | M4/WG
Release to supplier test DEWi sites |  | 2016-10-07 | M4/WG
Supplier version of completion notes released |  | 2016-10-07 | WG
Develop WNT 2017
Specification | 2016-05-03 | 2016-06-01 | WG
Draft specification release |  | 2016-06-01 | WG
Supplier review period | 2016-06-02 | 2016-07-05 | Suppliers
Version 1 specification release |  | 2016-07-05 | WG
Release validation CBDS |  | 2016-08-26 | WG
xslt development | 2016-08-30 | 2016-09-23 | WG
Draft fileset release |  | 2016-09-23 | WG
Supplier review period | 2016-09-23 | 2016-10-06 | Suppliers
Final fileset release |  | 2016-10-07 | WG
DEWi developments | 2016-08-30 | 2016-10-07 | M4/WG
Release to supplier test DEWi sites |  | 2016-10-07 | M4/WG
Supplier version of completion notes released |  | 2016-10-07 | WG
Summer SDF meeting
Software Development Forum meeting |  | 2016-06-01 | Suppliers/WG
DEWI user audit | 2016-09-05 | 2016-09-30 | WG
Autumn SDF meetings
Software Development Forum meeting* |  | 2016-10-11 | Suppliers/WG
Software Development Forum meeting* |  | 2016-11-15 | Suppliers/WG
CTF16 consultation | 2016-12-05 | 2016-12-30 | WG
*Potential to be cancelled